### Updated course information (2025 March 05th)

### 1. Scope of the course project

- Research idea development:

  - Current Knowledge -Literature review to summarize what is already known.

  - Identifying the Gap: Literature review to determine unanswered questions.

- Feasibility with EHR Analysis: Understand TriNetX EHR data and assess whether the research question can be answered using the data

- Methodology: Define how data will be extracted, analyzed, and interpreted.

- Results and Presentation: Conduct the analysis, present the project in ~15 min final oral presentation, design a poster for presentation in local or national conference (see below), and (optional but highly encourage) complete the manuscript preparation for submission for peer-reviewed publications

### 2.  Project Timeline & Milestones

March 30- July 30:  COM course period is roughly from March/April to May/early June; roughly 2 more months for continuing working on manuscript preparation.

Poster presentation for all projects at our 2nd Annual Research Day @ Department of Psychiatry!

| Week | Milestone | Deliverable | Lecture/Lab (Zoom) | Homework time needed * |
| --- | --- | --- | --- | --- |
| W1 | Project Initialization |  | 1hr/1hr | 1~5 hr |
| W2 | Define research question & scope |  | 1hr/1hr | 5~10 hr |
| W3 | Form research team |  | 1hr/1hr | 5~10 hr |
| W4 | Submit Compliance/IRB approval |  | 1hr/1hr | 5~10 hr |
| W5 | Complete preliminary literature review |  | 1hr/1hr | 10-20 hr |
|  | Finalize Statistical Analysis Plan (SAP) | SAP |  |  |
| W6 |  |  |  | 10-20 hr |
| W7-8 | Review preliminary results & internal (within team) presentation of SAP and results | Internal presentation (within team) | 1hr/1hr | 10-20 hr |
| W9 | Finalize results |  | 1hr/1hr | 10-20 hr |
| W10 | Oral & Poster Presentation (Psychiatry Research Day, Student Research Day, Beyond Research Day for residents) | Oral presentation (~20min each team) Poster submitted | Oral presentation in class (2hrs) ** | 10-20 hr |
| 11-15 |  |  | Open office 1hr/weekly *** | 1-5 hr |
| W16 | Manuscript submission | Finalized manuscript |  | 0-5 hr |

*Homework load varies by nature of the project. Students will be engaged in literature review, team building, research planning, completing analysis, preparing for oral and poster presentation and writing manuscript.

** Oral presentation is in person for students, the only session that requires physical attendance. It will also be in a hybrid format to allow other team members in the project to attend, including clinical/faculty mentor, resident lead and all of the research division in Psychiatry.

*** Open office will be offered via zoom weekly post course. It is not mandatory, but it is encouraged to take advantage of the hour so manuscript preparation can continue successfully.

### Other Team members & Responsibilities

### 1. Clinical Faculty Mentor (already confirmed mentors available for the available projects)

- Ensures clinical relevance of the project.

- Serve as a clinical content expert: assist in outcome and exposure definitions, ICD coding, procedure and medication definition and classification, etc

- Guides research methodology; Reviews results; Supports manuscript writing; coordinates publication.

### 2. Resident(s) Lead (ideally one resident to assist each medical student team)

- Acts as a bridge between the clinical mentor and medical students.

- Responsible for IRB submission.

- Also participates in literature review, research design, results interpretation, and manuscript writing.

### 3. Main Analytic Team: ~3 medical students who enrolled in the course

- Participates in research design & literature review; Leads the analytic protocol development

- Leads the analytic implementation on TriNetX, collecting data and results, present results in tables and graphs.

- Assists in manuscript writing and presentations.

- Required to complete a final oral and poster presentation for the course.

- While all three students participate in all aspects, each of the 3 students may take on a specialized role as bellows:

- Main Data Analyst:  Leads TriNetX analytics; Conducts data/result collection and additional analyses and visualization

- Project Coordinator: Oversees team coordination, communication and task completion; tracking milestone and deliverables; Ensures timely and accurate completion.

- Citation and documentation Manager:  Uses Endnote to maintain and track references; Maintains shared documents (SAP, presentations, and manuscript drafts), Ensures accurate citation and formatting for publication.

### 4. Other support and contact:

- Course director (Zhang-James)

- admin coordinator (Meg?),

- Other support: IRB, librarian (James Evans)