# Conference Planning Meeting

Friday, 04/18/2025
─
Attendees

Mary Jo, Lorraine, Mark, Rachel B., Sarah L., Michael, Rebecca, Kim, Jennifer

Absent: Rachel C., Sarah H., Liz

Note taker: Mary Jo

# Agenda & Notes:

## Last Meeting Follow-up

- Preliminary Schedule

  - Vendor content - presentations switched to earlier in the program each day and reduced to 10 minutes + Q & A (15 minutes max)

  - MLA Update and Region 7 update confirmed for Wednesday at 11:15 to Noon

  - Thursday afternoon schedule may change depending on member content

- Vendor Update

  - Registration for vendors is now live

  - Vendor trivia game - announce at beginning with questions upfront; answers at end on Thursday

  - Call for participation will go out next week

- Sub-Committees

  - Program Committee (responsible for member content)

    - Volunteers: Beth, Mary Jo

    - Next step: CAll for content will include new deadline of May 15th

  - Registration Committee (responsible for forms and tasks related to conference/CE registration)

    - Volunteers: Rachel C., Kim, Michael

    - Next Step: No update at this time

  - Communications Committee (responsible for advertising, and related)

    - Volunteers: Liz, Rebecca, Lorraine

    - Next Step: Add logo and send out call for content

- CE Update

  - Topic and Presenter: Dr. Foster is confirmed for Wednesday afternoon, 1:15 - 4:15 pm

  - Topic will be “critical conversations” but exact title TBD

- Logo

  - Done, but needs original UNYOC logo file to be embedded

  - Rebecca to reach out to her team to see if original logo file is available

    - Forward file to Lorraine for final adjustment

    - Lorraine to send finalized logo to

      - Michael for website

      - Jennifer and Mark for vendor communications

      - add it to the member communication going out next week.

## New Business

- Cost

  - Registration fee for virtual conference

    - $60 for members

    - $25 for students, or maybe complimentary?

- Web-based voting and trivia game

  - Consider slido.com for poll response

    - Check with Sarah H to see what Southeastern can support

  - Consider Kahoot for trivia responses

    - Jennifer and Mark to test

# Action Items

- Obtain UNYOC logo and update conference logo; post conference logo in google drive for all to access

- Communications team to send out update to member listserv -Week of April 21

- Call for participation/support to go out to vendors - Week of April 21

# Next Meeting Agenda Items

- Next Meeting:  May 16, 2025 at 10:00 AM